CONTRACTING AUTHORITY: Reta d.o.o., Zagrebačka 15 K, 47000 Karlovac, Croatia

PIN: 01201898816

SUBJECT OF PROCUREMENT: Wire drawing lines with training of employees

PROJECT ASSIGNMENT

INSTALLATION, COMMISSIONING, TRAINING, PERFORMANCE TESTS AND ACCEPTANCE CERTIFICATE

INSTALLATION

Contracting Authority is responsible for preparing suitable foundations and will proceed with the assembly and installation of the goods and make all the necessary connections of the goods at the premises of the Contracting Authority.

Tenderer shall provide to the Contracting Authority the necessary documentation (The Installation Instructions) to be strictly followed by the Contracting Authority for the installation of the wire drawing lines. The Installation Instructions required for the installation of the goods including foundations and electrical schemes shall be sent to Contracting authority by e-mail no later than two months before the estimated shipment of the goods, provided that the Contracting Authority paid the advanced payment in accordance with section 8. of this Invitation for submission of offers.

Contracting Authority will be solely responsible for the installation and will notify the Tenderer in writing about the end of the installation and readiness for the commissioning and training of employees.

Estimated time for installation is 1 (one) month from the shipping of goods.

COMMISSIONING

Tenderer is obligated to appoint Technicians who will carry out a check of the alignment of the components of the wire drawing lines, a check of the mechanical assembly and a check of the electrical connections in order to verify if the installation is done by the Contracting Authority in compliance with the Installation Instructions.

Tenderer will perform installation check and is obligated to promptly inform Contracting Authority in case of that the installation is not done in compliance with the Installation Instructions.

Any rectification of non – compliance in the installation including supplementary cost of Technicians is not part of subject of procurement of this Invitation for submission of offers and any supplementary cost of technicians appointed by Tenderer are not part of financial offer and will be determined additionally between Tenderer and Contracting Authority.

The commissioning includes start-up and trial operations.

Estimated  duration of the commissioning is 22 (twenty-two) business days.

TRAINING OF EMPLOYEES

After the commissioning, the technicians appointed by Tenderer will carry out the training of 6 (six) employees of Contracting Authority for the use of new technological solutions in regular production processes, specifically the use of PLC system built into the new drawing lines so that employees can use the acquired knowledge in managing and automating production systems and connecting machines that are part of the production process.

The duration of the training of employees is minimum 20 (twenty) business days.

Travel expenses, board and lodging costs arising during the effective performance of the commissioning and training are included in financial offer. Contracting Authority will organize transport of the technicians appointed by the Tenderer from the Hotel to Contracting Authority premises and back.

Any additional days and costs due to COVID-19 restrictions (e.g., mandatory quarantine or self-isolation) are not part of financial offer and will be determined additionally between Tenderer and Contracting Authority.

PERFORMANCE TESTS

After the commissioning, the Tenderer shall perform the performance tests that shall be previously agreed in writing with the Contracting Authority. If the wire drawing lines comply with the agreed performance tests, the wire drawing lines shall be considered automatically accepted by the Contracting Authority.

ACCEPTANCE CERTIFICATE

Contracting Authority and Tenderer will formalize full execution of subject of procurement by undersigning the Acceptance Certificate.

In accordance with section 2.4 of Invitation for submission of offers, the subject of procurement will be considered as delivered on the day when both wire drawing lines are delivered, commissioned, provided training of employees and final acceptance certificate is signed.

For the purpose of commissioning and training, Contracting Authority will provide as follows:

- During the whole period of the commissioning and training, the Contracting Authority will take care of the safety on the job site so that the work of the technicians appointed by the Tenderer is not carried out in an unhealthy or dangerous environment.

- The Contracting Authority will provide to the Tenderer availability of a Machine Operator for the operations of the wire string-up and as well a mechanical and an electrical engineer.

- The Contracting Authority will provide all the materials necessary during the whole period of the commissioning and training in due time, in sufficient quantity and of appropriate quality. In particular, wire rod, core, insulation material, oils and/or emulsions, dies, spools, baskets/carriers, wire pointers and welders, utilities (such as cooling water, compressed air, power supply, gas, etc.) will be available prior to the start of the commissioning and training.