Dilj industrija građevinskog materijala d.o.o., Vinkovci, Ciglarska 33, PIN: 60248788788, Republic of Croatia, represented by General Manager Dražen Ivezić (hereinafter referred to as: the Ordering Party) (phone number:                   e-mail address

and

_____________________________________________________________________________ (hereinafter refered to as: the Supplier), (phone number:             e-mail address:)

signed a

PROCUREMENT CONTRACT

for the Wet Pan Mill

SUBJECT OF THE CONTRACT

Article 1

Based on the conducted procedure of procurement for non-obligatory entities of Public Procurement Law, the Ordering Party has chosen the Supplier’s offer to conclude a contract for wet pan mill procurement as part of the project “Investment in energy efficiency measures and investment in promotion of energy from renewable sources of the company Dilj d.o.o.“ (procurement registration number DILJ-MF-01-22/ NOJN-01)

Article 2

In accordance with the Public procurement call and its appendixes from _____ and the offer No._____ as of___including appendixes all according to enclosed Bill of Quantity, the Supplier undertakes to deliver and provide technical assistance during installation of the Wet Pan Mill, ancillary equipment and documentation, as specified in Section 4.1. of Public procurement call.

The documentation stated in previous paragraph of this Article makes an integral part of the Contract.

The Supplier will execute the Contract in full and in compliance with Public Tender Invitation, chosen offer, Bill of Quantity and project documentation.

THE CONTRACT VALUE

Article 3

The value of the contract is:

Amount:		 	          _____________     (in words: ______________). (EUR/HRK in countervalue as of day of payment according to middle exchange rate of the Croatian National Bank) without VAT.

The price of the contract includes all of the Supplier’s expenses.

TERMS AND CONDITIONS OF PAYMENT

Article 4

After receipt of the guarantee for proper execution of the contract and guarantee for advance payment, The Ordering Party will pay following amounts to IBAN/SWIFT of the Supplier:

1. 30% of the total price of the contract as advance payment;

2. 50% of the total price of the contract after notification that the equipment is ready for delivery;

3. 10% of total price of the contract after successful installation and commissioning of the wet pan mill

4. 10% of total price of the contract after successful capacity proving of the wet pan mill

Upon receipt of the notice that the equipment is ready for delivery, and before executing payment, the Ordering Party has the right to determine the readiness of the equipment for delivery at the location of the Tenderer.

The Advance payment guarantee will be returned to the Supplier after the Wet Pan Mill is delivered to the Ordering Party’s premises.

PERSONS IN CHARGE

Article 5.

Both the Ordering Party and the Supplier will appoint a person in charge for signing the Minutes on successful handover.

The person in charge appointed by the Supplier will be obliged to present the working principles and give a short instructional demonstration of the Wet Pan Mill operation and ancillary equipment to the machine operators appointed by the Ordering Party’s person in charge who will be present during handover.

DELIVERY

Article 6

The delivery location is Dilj plant, Ciglarska 33, 32100 Vinkovci, Republic of Croatia

The delivery of equipment will be carried out according to terms of DAP (Incoterms®2020).

The Tenderer is obliged to insure the subject of procurement and to insure the insurance policy in favor of the Ordering Party and before paying 50% of the amount by the Ordering Party to submit proof of the concluded insurance policy to the Ordering Party.

The deadline for equipment delivery is given in the Article 15 of Public procurement call.

Within 90 days from signing of this contract The Supplier will deliver to the Ordering Party documentation of static-dynamic loads that are necessary for making of reinforced-concrete construction.

For every started week of delay in delivery of the wet pan mill, the Supplier will be charged with 0,5% of total price of the contract excluding VAT up to a maximum amount of 10% of contract value excluding VAT.

In  case if delay is longer than 10 weeks, the Ordering Party  will be entitled to collect the Advance payment guarantee and to terminate this contract by unilateral written declaration of will and choose another supplier.

The Supplier will be obliged to comply with applicable regulations when performing contractual duties and is solely responsible for the safety of its employees, compliance with regulations of the Republic of Croatia and the rules of conduct within the Ordering Party’s plant. In failing to do so, the Supplier bears responsibility for any damage to its employees, the Ordering Party , the Ordering Party’s   employees and third parties.

SUPPLIER’S GUARANTEES

Article 7

The Supplier will be obliged to provide and maintain a valid guarantee for performance and elimination of defects within the warranty period in accordance with the documentation referred to in Article 2 of this Contract and Public Tender Invitation.

The Supplier will be obliged to provide and maintain a valid Advance Payment guarantee in accordance with the documentation referred to in Article 2 of this Contract and Public Tender Invitation.

FINAL PROVISIONS

Article 8

The contracting parties agree that all disputes under this Contract will be resolved amicably, and in the event of a dispute, the court that will have jurisdiction is court with actual jurisdiction according to the seat of the Defendant.

The applicable Law on Obligations shall apply to everything that is not regulated by this Contract in an appropriate manner.

Article 9

This Contract is made in four equivalent copies, two copies for each contracting party, and is concluded on the date of signing by the contracting parties.

In Vinkovci, on __/__/ 2022

on behalf of the Ordering Party:	             			on behalf of the Supplier:

General Manager

Dražen Ivezić, dipl. ing.

_________________				                                    _________________