Dilj industrija građevinskog materijala d.o.o., Vinkovci, Ciglarska 33, PIN: 60248788788, Republic of Croatia, represented by General Manager Dražen Ivezić (hereinafter referred to as: the Ordering Party) (phone number:                   e-mail address

and

_____________________________________________________________________________ (hereinafter refered to as: the Supplier), (phone number:             e-mail address:)

in Vinkovci ___/___/2022. signed a

PROCUREMENT CONTRACT

for the Robot automated lines for setting, unsetting and packaging

SUBJECT OF THE CONTRACT

Article 1

Based on the conducted procedure of procurement for non-obligatory entities of Public Procurement Law, the Ordering Party has chosen the Supplier’s offer to conclude a contract for procurement of Robot automated lines for setting, unsetting and packaging as part of the project “Energy efficiency improvement and generation of electricity from renewable sources of the Dilj production plants“ ,procurement registration number DILJ-MF-01-22/ NOJN-02

Article 2

In accordance with the Public procurement call and its appendixes from _____ and the offer No._____ as of___including appendixes all according to enclosed Bill of Quantities, the Supplier undertakes to deliver and provide technical assistance during installation of the Robot automated lines as specified in Section 4.1. of Public procurement call.

The documentation stated in previous paragraph of this Article makes an integral part of the Contract.

The Supplier will execute the Contract in full and in compliance with Public Tender Invitation, chosen offer, Bill of Quantities and project documentation.

THE CONTRACT VALUE

Article 3

The value of the contract is:

Amount:		 	          _____________     (in words: ______________). (EUR/HRK in countervalue as of day of payment according to middle exchange rate of the Croatian National Bank) without VAT.

The price of the contract includes all of the Supplier’s expenses.

TERMS AND CONDITIONS OF PAYMENT

Article 4

After receipt of the guarantee for proper execution of the contract and guarantee for advance payment, The Ordering Party will pay following amounts to IBAN/SWIFT of the Supplier:

- 30% advance payment after signing the contract and after delivery of the Advance payment guarantee for the same amount,

- 30% advance payment 20 weeks after signing the contract and after delivery of the Advance payment guarantee for the same amount;

- 20% of the total price of the contract after signing the Minutes on successful preassembly and testing of equipment;

- 10% of total price of the contract after successful installation and commissioning of the robot automated lines

- 10% of total price of the contract after successful capacity proving of the robot automated lines.

The Advance payment guarantees will be returned to the Supplier after the complete equipment and documentation of robot automated lines is delivered to the Ordering Party’s premises.

If due to reasons on the part of the Ordering Party it is not possible to start installation and commissioning of the lines for more than 8 weeks, the Ordering Party will pay the Supplier 10% of the Contract value after the Supplier submits a bank guarantee valid until successful installation and commissioning, but no longer than 6 months. Bank guarantee shall be submitted in the original and must contain the following required information:

- That the beneficiary of the bank guarantee is the company Dilj d.o.o., Ciglarska 33, 32100 Vinkovci, Republic of Croatia

- That the bank, as a guarantor, unconditionally undertakes to pay the amount of 10% of contract value at the first call of the guarantee beneficiary and without objection if the Supplier does not successfully install and commission in accordance with Article 6 of this Contract.

PERSONS IN CHARGE

Article 5.

Both the Ordering Party and the Supplier will appoint a person in charge for signing the Minutes on successful handover.

The person in charge appointed by the Supplier will be obliged to present the working principles and give a instructional demonstration of the Robot automated lines operation and ancillary equipment to the machine operators appointed by the Ordering Party’s person in charge who will be present during handover.

DELIVERY

Article 6

The delivery location is Našice plant, B. Radića 200, 31500 Našice, Republic of Croatia

The delivery of equipment will be carried out according to terms of DAP (Incoterms®2020).

The Supplier is obliged to insure the subject of procurement and to insure the insurance policy for transport of goods in favor of the Ordering Party and before paying 20% of the amount by the Ordering Party to submit proof of the concluded insurance policy to the Ordering Party.

The deadlines for equipment delivery, installation and commissioning works and other conditions of delivery, storage and completion of works are given in the Item 15 of Public procurement call.

Prior to the delivery of the equipment, the Supplier is obliged to perform pre-assembly and successful testing of the equipment at its location in the presence of the Ordering Party's representative, about which a Minutes on successful preassembly and testing of equipment will be made.

Within 120 days from signing of this contract Supplier will deliver to the Ordering Party documentation necessary for the construction from Item 4.1 of Public procurement call.

For every started week of delay in delivery or in works of installation and commissioning of the robot automated lines, the Supplier will be charged with 0,5% of total price of the contract excluding VAT up to a maximum amount of 10% of contract value excluding VAT.

In case if delay is longer than 10 weeks, the Ordering Party will be entitled to terminate this contract by unilateral written declaration of will, choose another supplier and collect the advance payment guarantee.

The Supplier will be obliged to comply with applicable regulations when performing contractual duties and is solely responsible for the safety of its employees, compliance with regulations of the Republic of Croatia and the rules of conduct within the Ordering Party’s plant. In failing to do so, the Supplier bears responsibility for any damage to its employees, the Ordering Party, the Ordering Party’s employees and third parties.

SUPPLIER’S GUARANTEES

Article 7

The Supplier will be obliged to provide and maintain a valid guarantee for performance and elimination of defects within the warranty period in accordance with the documentation referred to in Article 2 of this Contract and Public Tender Invitation.

The Supplier will be obliged to provide and maintain a valid Advance Payment guarantee in accordance with the documentation referred to in Article 2 of this Contract and Public Tender Invitation.

FINAL PROVISIONS

Article 8

The contracting parties agree that all disputes under this Contract will be resolved amicably, and in the event of a dispute, the court that will have jurisdiction is court with actual jurisdiction according to the seat of the Defendant.

The applicable Law on Obligations shall apply to everything that is not regulated by this Contract in an appropriate manner.

Article 9

This Contract is made in four equivalent copies, two copies for each contracting party, and shall enter into force on the date of its conclusion.

In acceptance of the above provisions, the Contracting Parties sign this Contract.

on behalf of the Ordering Party:	             			on behalf of the Supplier:

General Manager

Dražen Ivezić, dipl. ing.

_________________				                                    _________________